## Sample Data Migration Guide
OptimalData
NetSuite Project Plan
As of July 2024
| How to use this guide: | This guide shares common data migration tasks in a NetSuite implementation. The tasks are ordered as they need to be completed with an approximate timing within the context of an implementation. The "Helpful links" section, where applicable, provides links to OptimalData's content, which provides additional details on how to complete these tasks.
| Area | High-Level Task Checklist | Description | Helpful links | Common Source File in Legacy System | Approximate Timing
| Load Master Records | Load GL accounts | Prepare the CSV import template for your general ledger (GL) accounts | How to import accounts from QuickBooks to NetSuite | Chart of Accounts | Completed in the first 15 days of the project
|  | Load department/class/location segments | Prepare the CSV import template for your other segments. Note - if there are less than 10 values, consider adding manually | Intentionally blank | Department/Class/Location list | Completed in the first 15 days of the project
|  | Load item records | Prepare the CSV import template for your items | Intentionally blank | Item Master | Completed in the first 15 days of the project
|  | Load customers and vendors | Prepare the CSV import templates for your customer and vendor records. Note that the resources are mostly applicable to both customers and vendors | How to import vendors from QuickBooks Online to NetSuite | Vendor/Customer contact list | Completed in the first 15 days of the project
Best practices for importing vendor records to NetSuite
| Build Segment Map File | Build the segment map file | Prepare a map file showing how the legacy segment values correspond to the new NetSuite segment values. | How to prepare a segment map file | N/A | Completed while loading the master records or right after
| Load Summary Financials | Load the first batch of historical trial balances | Prepare, load, and validate the historical trial balances for the first batch of data. The first batch of data should be from the earliest date you are importing financials through the most current locked period. You don't want to import any financial data that might change. | Step by step checklist: Load financials and open transactions from QuickBooks to NetSuite | Either a GL transaction list or the trial balance; see article "Two ways to prepare historical monthly financials in NetSuite" | Completed in the middle of the project
|  | Load the final batch of historical trial balances | Load the remaining historical financial statements. This should be from the last date loaded in the above step through the go-live date. Do not start this step until you've locked the legacy accounting system. | Two ways to prepare historical monthly financials in NetSuite | See above | Right before the go-live date
| Load Open Transactions | Load new customers and vendors | Prepare the CSV import templates for any new customers or vendors created since this was completed at the beginning of the project | See link above under "Load customers and vendors" task | See above | Completed the last week of the project
|  | Load new items | Prepare the CSV import templates for any new items created since this step was completed at the beginning of the project | Intentionally blank | See above | Completed the last week of the project
|  | Refresh the segment map file | Add any new master records created to the segment map file so you can quickly prepare and load the open transaction imports | See link above under the "Build Segment Map FIle" | N/A | Completed the last week of the project
|  | Load open accounts payable transactions | Load the open accounts payable (AP) balances as of the go-live date. This should be completed after you've locked the legacy accounting system right before the go-live date | How to import open AP transactions into NetSuite | Detailed AP aging report | Right before the go-live date
|  | Load open accounts receivable transactions | Load the open accounts receivable (AR) balances as of the go-live date. This should be completed after you've locked the legacy accounting system right before the go-live date | How to import open AR transactions into NetSuite | Detailed AR aging report | Right before the go-live date
|  | Load open inventory | Load the open inventory balances as of the go-live date | Intentionally blank | Physical inventory reports | Right before the go-live date
|  | Load open purchase orders | Load the open PO lines as of the go-live date. This should be completed after you've locked the legacy accounting system right before the go-live date. Note that for partially fulfilled PO's, you should only import the remaining balance. | How To Import Open Purchase Orders From QuickBooks into NetSuite | Detailed open purchase order report | Right before the go-live date
|  | Load open sales orders | Load the open SO lines as of the go-live date. This should be completed after you've locked the legacy accounting system right before the go-live date. Note that for partially fulfilled SO's, you should only import the remaining balance. | Intentionally blank (similar process to the purchase orders) | Detailed open sales order report | Right before the go-live date
|  | Load open bank transactions | Load the open bank transactions that haven't cleared the bank or credit card reconciliation. | How to import open bank transactions into NetSuite | Last completed bank reconciliation | Can be completed post-go-live
OptimalData Consulting offers a step-by-step course for companies moving from QuickBooks Online to NetSuite. Its available for $400 at the link below
Link to QBO to NetSuite course
Do you wish someone would help you migrate your data to NetSuite? Guess what, OptimalData Consulting can help you. Reach out today for a free estimate!
Paul Giese ¦ paul@optimaldataconsulting.com ¦ (617) 645-6100 ¦ www.optimaldataconsulting.com